## Sheet1
Start Date | End Date | Phase Name | Description | Duration(days)
2021-10-03 | 2022-02-15 | Research | Research Phase | 135
2021-10-31 | 2021-11-20 | Desing | Design GUI | 20
2021-11-14 | 2021-12-01 | GUI Skeleton | Code GUI skeleton to start adding the functions to the program | 17
2021-12-02 | 2021-12-25 | First Function | Code the usages times function | 23
2021-12-14 | 2021-12-27 | Individual Testing / Fix | Test the first function and if have errors correct it. | 13
2021-12-27 | 2022-01-21 | Second and Third Function | Code the schedule function and program lock function | 25
2022-01-03 | 2022-01-27 | Functions Testing /Fix | Test the 2 last functions, and if the have errors correct it. | 24
2022-01-24 | 2022-02-21 | Finalize the GUI | Add the Themes to the GUI, and stylize it. | 28
2021-12-27 | 2022-03-05 | User Test | Test the program in its entirety and give it as a beta program to some selected users with the purpose of testing it | 68
2022-03-07 | 2022-03-15 | Fix | Fix all the possible errors that the program may have | 8
Formulas:
Duration(days) = DAYS([End Date],[Start Date])